## ProjectData
Project Name | Select Values | Full DT | Lean UX | Presale | Website | Waterfall | Minimal
Project Type | Presale/Proposal | Y | N | Y | Y | N | N
Engagement Onsite | No | N | Y | N | Y | Y | Y
Dev Complexity | Low | N | Y | N | Y | N | Y
Project Scope | Large | Y | N | Y | N | Y | N
Receivables Input | Inadequate | N | N | N | Y | N | Y
Business Importance | High Value Customer | Y | Y | Y | Y | Y | Y
Client Expectations | MVP | N | Y | Y | Y | N | Y
Time Constraint | 2-3 Weeks | N | Y | Y | Y | N | Y
Project Budget | Low | N | Y | N | Y | N | Y
Business Goals | Modernization | Y | Y | Y | Y | Y | Y
Available Resources | Minimal | N | Y | N | Y | N | Y
Notes:
All project attributes have equal weight. As such, the column/s with the most "Ys" will be the best process methodology fit. Use this at input to filter/select the applicable activities on the "UX_Activities" tab

## UX_Activities
# | Activity | Mapping, Notes & References | Deliverables | Full DT | Lean UX | Presale | Website/CMS | Waterfall | Minimal
Plan | (Pre Project Kickoff)
ACT_001 | Project Planning, Definition, Scoping | Project Type, Constraints, Complexity, Resources, Scope Decide on "Kit" - Mix of activities (This Excel) Design Brief includes: Project Description, Intent Scope, Exploration Questions, Target Users, Research Plan, Expected Outcomes, Success Metrics, Project Planning. Design Research Plan: Who we will study?, Where we will find them?, What questions/issues will we explore?, How many contacts?, Timeline, Team member responsible | UX_Excel_Template | Y | Y | Y | Y | Y | Y
ACT_002 | Effort/Estimates, R&Rs, RFP Development |  | UX_Excel_Template | Y | Y | Y | Y | Y | Y
ACT_003 | Request Inputs/Receivables | existing system/app, user guides, previous UX studies, system architecture, business processes, data model, operational stats | Email Correspondence | Y | Y | Y | Y | Y | Y
ACT_004 | Problem Statement | Initial problem per client. "Napkin" Pitch: Concept Name, The big idea, Needs/Benefits, Execution and Business Case | Proposal Template | Y | Y | Y | Y | Y | Y
ACT_005 | Define Goals & Expectations | Business Goals, UX Goals KPIs, OKRs, Usability Benchmarking, Metrics, Measurements | Proposal Template | Y | Y | Y | Y | Y | Y
ACT_006 | Presale Business Case - ROI | Measure the delta between existing and recommended and apply it to a) frequent tasks and b) KPIs | Proposal Template | Y | N | Y | N | N | N
Discovery Research | Explores current reality, and focuses on the current problem or challenge we’re trying to solve. It includes paying attention to what customers are struggling with, what frustrates them and what trade-offs they’d rather not have to be making. What is includes Research, Identify Insights and Establish Design Criteria. Considers an idea’s potential for value creation. As part of this analysis, we need to assess our own organization’s capabilities and resources.
ACT_007 | User/Customer Research - Shadowing | Reveal opportunities and show how product might affect/complement users' behavior Shadow someone to observe routines/interactions/context | U_Review | Y | N | Y | N | N | N
ACT_008 | User/Customer Research- Contextual Interviews | Get insight from their answers and their environment Interview people in their natural environments | U_Review | Y | Y | Y | N | N | N
ACT_009 | User/Customer Research- End user observations | Side-by-sides | UX_ExcelTemplate | Y | Y | Y | N | Y | N
ACT_010 | User/Customer Research - Guided Tours | (of client/customer) operational environment | UX_ExcelTemplate | Y | Y | Y | N | N | N
ACT_011 | User/Customer Research - Card Sort | Understand people's mental models of a device/system and expectations/priorities about intended functions On separate cards, name possible features, functions, or design attributes. Ask people to organize spatially | U_Review | Y | N | N | N | N | N
ACT_012 | User/Customer Research - A Day in the Life | Reveal unanticipated issues inherent in user's everyday routines/circumstances Catalog activities and contexts throughout a full day | U_Review | Y | Y | Y | N | N | N
ACT_013 | User/Customer Research - Competitive Solutions | competitor analysis | Proposal Template | Y | Y | Y | N | N | N
ACT_014 | User/Customer Research - Surveys & Questionnaires | Includinhg still photo survey Quickly get information from many people | Proposal Template | Y | N | Y | N | N | N
ACT_015 | User/Customer Research - Identify Insights | Insights and Design Criteria | UX_ExcelTemplate | Y | Y | Y | Y | Y | Y
ACT_016 | User/Customer Research - SUS/SUMI | User satisfaction | UX_ExcelTemplate | N | N | Y | N | Y | N
ACT_017 | User/Customer Research - Online Research | Including literature reviews |  | Y | Y | Y | Y | N | N
ACT_018 | User/Customer Research - Contextual Inquiry | Cultural, Physical, Artifacts, Communications | Proposal Template | Y | N | Y | N | N | N
ACT_019 | User/Customer Research - Clickstream Analysis |  | U_Review | Y | N | Y | Y | N | N
ACT_020 | Requirements / User Stories | Typically in collaboration with Business Analyst (Product Manager) | UX_ExcelTemplate | Y | Y | Y | N | Y | N
ACT_021 | Scenarios of Use / Use Cases | Context Scenario - probable cases of use per persona | UX_ExcelTemplate | Y | Y | Y | Y | Y | Y
ACT_022 | Content Analysis |  | U_Review | Y | N | N | Y | Y | N
ACT_023 | Personas and Points of View | Including chracter profiles | Proposal Template | Y | Y | Y | Y | Y | Y
ACT_024 | Expert Usability Review of existing system | Heuristic Evaluation, standards, consistency | U_Review | Y | Y | Y | Y | N | N
ACT_025 | Branding & Style Guide |  | VisualDesign | Y | Y | N | Y | N | N
ACT_026 | Business Processes | Where available. If required and unavailable, must be developed by design | UX_ExcelTemplate | Y | Y | Y | N | Y | N
ACT_027 | Journey mapping - Current Solution |  | UX_ExcelTemplate | Y | Y | Y | N | N | N
ACT_028 | Technology & Constraints |  |  | Y | Y | Y | Y | Y | N
Analysis | We start to consider new possibilities, trends and uncertainties and envision what a desirable future might look like. Here, we Brainstorm, Develop Concepts and Create Pitches. Leverages what we’ve learned in the first stage to imagine these possibilities. Takes the wealth of ideas generated in stage two and culls them down to a manageable number. We do so by looking for those that pack a potential “wow,” that hit the sweet spot of solving the customer’s problem elegantly while also offering attractive profit potential. This is an iterative process, utilizing the scientific method to work through hypotheses and potential outcomes
ACT_028 | Journey Mapping - Recommended Solution | Design Scenario |  | Y | Y | Y | Y | Y | Y
ACT_029 | Storyboarding |  |  | Y | N | N | N | N | N
ACT_030 | Initial Concepts | Desired end-state, business concepts |  | Y | Y | Y | Y | N | N
ACT_031 | Brainstorming |  |  | Y | Y | N | Y | N | Y
ACT_032 | Participatory /Collaborative Design | participants help in creating design |  | Y | Y | Y | Y | Y | N
ACT_033 | Test Assumptions | Test Assumptions, evaluate assumptions, which concepts/ideas hit the "sweet spot"? What trade-offs are necessary and the value matches our resources, capabilities and deliver the offering |  | Y | Y | N | N | N | N
ACT_034 | Low Fidelity Prototyping | Paper prototype or sketch |  | Y | Y | Y | N | N | Y
Design | we take what we’ve learned from the analytical thinking we did in stage three and build a low-fidelity prototype. We then solicit customer feedback, and use it to build a high-fidelity prototype. We can then take this semi-finished product to small groups of customers to see if they perceive sufficient value in it. At this stage, customer co-creation is a valuable way to reduce the risks of new product development, by enabling customers to help design it
ACT_035 | User Story (Use Case) Analysis | frequent tasks analysis, operational stats, etc. |  | Y | Y | Y | N | Y | N
ACT_036 | Interaction Design | ITERATIVE: Including Task Analysis |  | Y | Y | Y | Y | Y | Y
ACT_037 | Wireframes | ITERATIVE |  | Y | Y | Y | N | Y | N
ACT_038 | Medium Fidelity Prototype | HTML with links , but not finished visual design and not connected on the back end |  | Y | Y | Y | N | N | N
ACT_039 | Concepts for Visual Mood |  |  | Y | Y | Y | Y | N | N
ACT_040 | Mockups | Hi Fidelity visual design (static graphics) |  | Y | Y | Y | Y | Y | Y
ACT_041 | Content Management |  |  | Y | Y | N | Y | N | N
ACT_042 | Design Reviews | Collaborative Walkthroughs |  | Y | Y | Y | Y | Y | Y
ACT_043 | Collaborative Stakeholder Reviews |  |  | Y | Y | Y | Y | Y | Y
ACT_044 | Cognitive Walkthrough | Think Aloud Protocol |  | Y | Y | Y | Y | N | N
Validate
ACT_045 | Refine Use Cases |  |  | Y | Y | Y | N | Y | n
ACT_046 | Default Values and States, Valid Values |  |  | Y | Y | Y | Y | Y | y
ACT_047 | User Assistance | UI driven (e.g,. Indicators…) |  | Y | Y | Y | Y | Y | N
ACT_048 | Interaction Design Documentation |  |  | Y | N | N | N | N | N
ACT_049 | Visual Design Documentation |  |  | Y | N | N | N | N | N
ACT_050 | User Testing | Performed on functioning site, prototype, wireframe Also first click testing and identifies user frustrations with site during 1 on 1 sessions. User performs tasks on-site |  | Y | Y | N | Y | Y | N
ACT_051 | A¦B Testing | Testing alternate design solutions |  | Y | Y | N | Y | N | N
ACT_052 | User Acceptance Criteria | Standards (ISO, IEEE, W3C, Accesibility, etc.) |  | Y | Y | Y | Y | Y | N
Deliver
ACT_053 | Application Help Documentation |  |  | Y | Y | Y | Y | Y | N

## Estimates
Account Name / Project Name - UX Effort/Estimates
User | Function | Source | Complexity | Pages | Effort in person days |  |  |  | Total
[5 empty] | UX | Visualization | UI_Dev | Reviewer
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
|  |  | TOTALS |  | 0 | 0 | 0 | 0 | 0