## Slide 1
Phases and Deliverables
Project Kick-off, Discovery & Planning
PHASE 1
Data Collection
PHASE 2
Assessment and Recommendations
PHASE 3
Final Report Presentation
PHASE 4
Detailed Plan for Data Gathering & Project Management
User Interview Protocol
Survey questionnaire
Summary Report with key insights from data gathering
Summary Report with issues in current intranet and stakeholder vision for intranet
Assessment and Recommendations Report Draft
Raw Data
Final Assessment and Recommendations Report Draft
DELIVERABLES
DELIVERABLES
DELIVERABLES
DELIVERABLES

## Slide 2
Project Kick-off, discovery & planning
PHASE 1
Our Approach
1
Kick-off Onsite Meeting with Client
Deliverables
Detailed Plan for Data Gathering & Project Management
Duration
3 Weeks
2
Understand the current solution, structure, roles and global footprint
3
Define target personas and who will represent success metrics
4
Develop Plan and templates to gather data using qualitative and quantitative methods
5
Understand Technical Architecture, projects and initiatives
User Interview Protocol
Survey questionnaire
Location
[Location]
* Identify Extreme and Mainstream Users

## Slide 3
WEEK 1
W2 W3 W4 W5 W6 W7 W8 W9 W10 W11 W12
Project Kick-Off
Closure
Data Collection
Assessment and Recommendations
Final Report
Presentation
MILESTONE 1:
Data Gathering Plan
Data Gathering
Protocols
MILESTONE 2:
Summary Report covering key insights, Content Strategy
MILESTONE 3:
Full User Needs Assessment Report w/ Recommendations
MILESTONE 4:
Final Report
and
Presentation
Conduct interviews, surveys, contextual inquiry
Analyze Data
Initial Discovery & Planning
Timeline
PHASE 1
PHASE 2
PHASE 3
PHASE 4
Assessment starts here
Overlap between phase 2 and phase 3

## Slide 4
WEEK 1
W2 W3 W4 W5 W6 W7 W8 W9 W10 W11 W12
Resource-wise Timeline
Project Kick-Off
PHASE 1
Data Collection
PHASE 2
Assessment and Recommendations
PHASE 3
Final Report Presentation
PHASE 4
UX Strategist & Manager
UX Researcher
UX Researcher
Content Strategist
Technical Manager
Technical Expert

## Slide 5
Phase | Milestone | Timeline
1 | Project Kick-Off, Discovery & Planning | End of 3rd Week
2 | Data Collection | End of 7th Week
3 | Assessment & Recommendations | End of 10th Week
4 | Final Report Presentation & Project Closure | End of 12th Week
 | Total Duration | 12 Weeks
 | Total Cost | US$ XXX,XXX
This is a Fixed Price proposal. Based on requirements received, below are the timeline and cost. Changes to requirements may result in an increase in time, cost, or both.
Pricing
Note:
This cost does not include travel, accommodation and any other incidental costs.
These expenses will be billed separately at actuals.